## db
Workstream | Task | Owner | Latest Update | Status | Priority | Due Date | Escalation | Blocker | Next Step
Zurp | Custom clearence required for Product A | Logistics | 4 day delay to leave from Shenzen. Forwarded on hold. | Blocked | Urgent | ASAP | Yes | Freigh forwarded has stated missing commercial invoice | Supply Chain to send invoice
Zurp | Mass production of packaging | Supply | Supplier has packaging samples, on hold for further details. | Blocked | Urgent | ASAP | Yes | Needs dimensions, barcodes, carton count, address and insert card approval | Approve insert card & send specs to supplier
After Ours | Landing page | Dev | Landing page pushed to production. | On Track | High | Complete | No | - | Monitor traffic & patch bugs
After Ours | Checkout trigger bug on Safari brower | Dev | Checkout button fails on mobile Safari. | Urgent | Urgent | Today | Yes | Bug is live in production. | QA Test and patch update.
After Ours | Product B - subscription option | Dev | Subscription option disappears after a variant is selected. | Delayed | High | Today | No | Variant logic breaking UI | Investigate and fix variant JS logic
Zurp | Discount code failures | Support / Dev | 12 user cases reported on failed discount codes not being applied. | Delayed | High | Today | No | Possible backend code configuration | Support/Dev to test on all platforms to identify the issue
Marketing | Final product photos for launch ads and email flows | Marketing | Blocks launch ads and email flows. | Urgent | High | Friday | Yes | Vendor has been unresponsive for the past 48 hours | Call vendor directly / Escalate
Marketing | Assets for Paid Media | Marketing | Paid media team is on standby. | Blocked | Medium | TBD | Yes | Needs final URL, claims, images, launch date | Complile launch info packet
After Ours | Assign Project Owners | N/A | Need owners for: 1) QA site checklist 2) Email/SMS copy review. | Decisions needed | High | Today | Yes | Awaiting executive decision | Nik/Rameez to assign owners